MyPA

Your Personal & Business AI Assistant

Project Plan & Release Roadmap

Version 1.0

20 July 2026

Status: Draft for Review

# 1. Purpose

This document sequences MyPA Phase 1 into concrete build phases with estimated durations, deliverables, dependencies, and the team roles needed — turning the BRD, Architecture, FDD, and TDD into an executable plan. Estimates assume a small dedicated team (roughly 2-3 engineers, 1 designer, 1 QA, part-time PM) and should be recalibrated once the actual team is staffed.

# 2. Phase Overview

| Phase | Name | Est. Duration | Goal |
| --- | --- | --- | --- |
| 0 | Foundation | 2-3 weeks | Flutter + Supabase project scaffolded across all 6 platforms; CI/CD pipeline running |
| 1 | MVP AI Core | 3-4 weeks | Guided content creation, Prompt Library, and one social platform live end-to-end |
| 2 | Voice Layer | 1-2 weeks | Speech-to-text and text-to-speech integrated across the creation flow |
| 3 | Multi-Platform Integrations | 3-5 weeks | Remaining 4 social platform adapters (LinkedIn, X, TikTok, YouTube), repurposing, scheduling |
| 4 | Admin & Team Features | 2-3 weeks | Team/role management, quotas, approval workflow, brand asset library |
| 5 | Documentation & QA Hardening | 2 weeks | User Guide, Prompt Library, Troubleshooting Guide finalized; full test pass per Test Plan |
| 6 | Polish & Launch | 1-2 weeks | UAT sign-off, store submissions, production deploy |

Total estimated timeline: approximately 14-21 weeks depending on team size and how much of the 5-platform integration work (Phase 3) runs in parallel versus sequentially, and pending each social platform's own API approval turnaround (see Section 5).

# 3. Phase Detail

## Phase 0 — Foundation

- Set up GitHub monorepo structure (Architecture Document Section 11).

- Scaffold Flutter app with Riverpod, layered folder structure, and platform-adaptive navigation shell (FDD Section 1).

- Provision Supabase project; apply initial schema migrations (TDD Section 3).

- Stand up GitHub Actions CI/CD across all 6 build targets (Architecture Section 12).

- Deliverable: a signed-in-only 'empty shell' app running on all 6 platforms from one commit.

## Phase 1 — MVP AI Core

- Implement Core Platform: sign-up/login, account type selection, subscription tier display.

- Implement ai-generate Edge Function with paid-tier-only entitlement gating (TDD Section 5, 6.1).

- Implement Create screen (guided 3-step) and Prompt Library screen (FDD Section 3.2).

- Implement one social platform adapter (recommend Meta/Instagram first — highest individual-user relevance) end-to-end: connect, publish.

- Deliverable: an individual user can sign up, upgrade, create an AI post, and publish it to one platform.

## Phase 2 — Voice Layer

- Integrate platform-native STT/TTS across Create and content review screens (Architecture Section 7).

- Add voice capture overlay and playback controls (FDD Section 4.2).

- Deliverable: voice input/output works consistently on all 6 platforms.

## Phase 3 — Multi-Platform Integrations

- Implement remaining adapters: LinkedIn, X, TikTok, YouTube (TDD Section 7).

- Implement Repurpose screen and Content Calendar (FDD Section 3.2).

- Build in manual-export fallback for any platform whose API approval is still pending (per BRD risk register).

- Deliverable: one idea can be repurposed and scheduled across all 5 launch platforms.

## Phase 4 — Admin & Team Features

- Implement Team Workspaces, roles, and RLS-enforced permissions (TDD Section 3.3, 4.2).

- Implement Usage & Quotas, Approval Workflow, and Brand Asset Library screens (FDD Section 5.2).

- Deliverable: a business account can invite a team, set quotas, and require approval before publishing.

## Phase 5 — Documentation & QA Hardening

- Finalize User Guide, Prompt Library, and Troubleshooting Guide against the shipping build (not the design draft).

- Execute the full Test Plan (all test cases, all 6 platforms, security checklist).

- Deliverable: exit criteria from the Test Plan Document Section 4.2 fully met.

## Phase 6 — Polish & Launch

- Run UAT with persona representatives (Test Plan Section 9).

- Submit to Google Play, Apple App Store/TestFlight, Mac App Store or notarized build, Microsoft Store or signed installer.

- Deliverable: MyPA Phase 1 live in production on all 6 platforms.

# 4. Team Roles Needed

| Role | Primary Responsibility |
| --- | --- |
| Flutter Engineer(s) | Client app across all 6 platforms; UI, state management, platform adaptivity |
| Backend Engineer | Supabase schema, RLS policies, Edge Functions, social platform adapters |
| Product Designer | Visual design layer on top of the FDD's functional wireframes; brand system |
| QA Engineer | Executes the Test Plan; cross-platform regression; UAT coordination |
| Technical Writer | Finalizes User Guide, Prompt Library, and Troubleshooting Guide against the shipping build |
| Project Manager (part-time) | Sequencing, dependency tracking, stakeholder communication |

# 5. Key Dependencies & Schedule Risks

| Dependency | Schedule Risk | Mitigation |
| --- | --- | --- |
| Apple Developer Program enrollment | Can take days to process if not already active | Start enrollment in Phase 0, in parallel with scaffolding |
| Social platform API approvals (esp. TikTok) | Approval timelines are outside MyPA's control and can lag Phase 3 | Sequence Meta/LinkedIn/X first (typically faster); build TikTok's manual-export fallback so Phase 3 isn't blocked |
| OpenAI API account/quota setup | Blocks all of Phase 1 if delayed | Confirm access before Phase 0 ends |
| macOS build runner availability | iOS/iPadOS/macOS builds need Mac hardware | Confirm GitHub-hosted macOS runner capacity or provision a self-hosted Mac in Phase 0 |

# 6. Post-Launch Roadmap (Phase 2 of the Product, Beyond This Plan)

Captured for continuity with the BRD's roadmap section — not part of this release's scope or timeline:

- AI Personal/Business Assistant Core: reminders, tasks, general-purpose assistant chat (BR-PA-01, BR-PA-02).

- Deeper native analytics and predictive trend detection.

- Additional language support.